## Task Sheet
SDLC Platform — Mentor Task Sheet
Daily development & implementation log up to July 24, 2026 (Excluding Weekends)
S.No. | Date | Task Name / Description | Status
1 | 11/6/2026 | Initiated research and introductory brainstorming on the multi-agent SDLC workflow structure. | Completed
2 | 12/6/2026 | Conducted research and competitive analysis on existing SDLC platforms for reference as per provided documentation. | Completed
3 | 15/6/2026 | Studied Agentic AI concepts, agent interactions, and design patterns for pipeline automation. | Completed
4 | 16/6/2026 | Presented the reference analysis document on existing SDLC platforms. Received and completed workflow diagram task. | Completed
5 | 17/6/2026 | Designed Landing Page & Workspace Selection screens; defined initial user flow and screen layout structure. | Completed
6 | 18/6/2026 | Completed remaining platform screens, finalizing 10 UI screens for Multi-Agent SDLC Platform prototype readiness. | Completed
7 | 19/6/2026 | Reviewed implementation flow based on finalized UI designs; set up initial frontend structure & requirement backend. | Completed
8 | 22/6/2026 | Finalized Phase 2 backend modules including LLM integration, requirement extraction, and business analysis workflows. | Completed
9 | 23/6/2026 | Reviewed existing SDLC pipeline and analyzed agent orchestration flow for inter-agent communication & artifact passing. | Completed
10 | 24/6/2026 | Integrated Requirement Agent and Business Analysis Agent outputs for structured artifact transfer. | Completed
11 | 25/6/2026 | Focused on Database Agent integration and storage layer handling; improved schema flow & artifact persistence. | Completed
12 | 26/6/2026 | Worked on Architecture Agent integration and optimized dependency mapping between architecture, database, & UI/UX workflows. | Completed
13 | 29/6/2026 | Analyzed new workflow requirements and planned Video Agent integration flow within existing pipeline. | Completed
14 | 30/6/2026 | Started Video Agent development, defining artifact-to-video visual explanation flow & module sequencing. | Completed
15 | 1/7/2026 | Refined Video Agent content flow, explanation structure, and interactive video output mapping. | Completed
16 | 2/7/2026 | Started Frontend Agent integration, connecting with Requirements, Architecture, & Database artifacts. | Completed
17 | 3/7/2026 | Strengthened Frontend Agent integration with live preview, component mapping, and refinement features. | Completed
18 | 6/7/2026 | Integrated Backend Agent modules (FastAPI, SQLAlchemy ORM, Async Uvicorn server) with Frontend workspace endpoints. | Completed
19 | 7/7/2026 | Implemented Security & Compliance Agent workflows (SOC 2, ISO 27001, OWASP ASVS Level 2, Fernet key encryption). | Completed
20 | 8/7/2026 | Developed Testing Agent framework for automated test suite generation, coverage tracking, & integration test execution. | Completed
21 | 9/7/2026 | Developed Documentation Agent and integrated ReportLab PDF generator for enterprise BRD/SRS document compilation. | Completed
22 | 10/7/2026 | Integrated BYOK (Bring Your Own Key) Multi-Provider settings UI supporting Azure OpenAI, OpenAI, Claude, and local Ollama. | Completed
23 | 13/7/2026 | Implemented Governance & Approval Matrix center for multi-stage artifact sign-off across the SDLC pipeline. | Completed
24 | 14/7/2026 | Integrated Temporal Replay & History Center for state trajectory tracking and time-travel debugging of agent runs. | Completed
25 | 15/7/2026 | Developed Dashboard & Live Analytics center with real-time project telemetry, agent indicators, & pipeline metrics. | Completed
26 | 16/7/2026 | Conducted full-stack integration testing, resolving CORS authentication, API routing, and state synchronization. | Completed
27 | 17/7/2026 | Implemented BACopilot and Requirements Copilot interactive assistants for live requirement mutation & synchronization. | Completed
28 | 20/7/2026 | Refactored brd_srs_builder.py and pdf_generator.py to enforce Single Source of Truth architecture reading directly from PostgreSQL DB. | Completed
29 | 21/7/2026 | Developed automated repository scanner (create_setup_guide_excel.py) and generated SDLC_Platform_Local_Setup_Guide.xlsx. | Completed
30 | 22/7/2026 | Executed strict end-to-end runtime verification suite (run_srs_brd_strict_verification.py) for SRS & BRD PDFs under Copilot mutations. | Completed
31 | 23/7/2026 | Managed Git version control, creating feat commit 06250e3 and pushing verified source code cleanly to remote GitHub repository. | Completed
32 | 24/7/2026 | Polished UI contrast, search & filter input visibility (bg-slate-900), icon refinement, and committed changes to local repo (56a074b). | Completed